## Sheet1
Name | Email | Task | Duration | Dependency | Due Date | Note
Sang Kim | skim262@student.gsu.edu | Coordinator, Slack setup | 45 minutes | Slack | Slack :1/30/2020 | invite members to slack. sinkorfloat.slack.com
Maria Juarez | mjuarezgaytan1@student.gsu.edu | Final Report | 1 hour | Slack, Github | 2020-02-06 | Using the resources to write a final report
Gayoung Kim | gkim70@student.gsu.edu | Raspberry Pi Instructions, Assisting Other members |  |  | 2020-02-06 | Assist other members with assigned work.
Woosung Lee | wlee40@student.gsu.edu | Raspberry Pi Instruction,Youtube Cannel | 30 Minutes | Youtube | 2020-02-03 | Create a youtube channel before shooting a video
Andrew Ballard | aballard3@student.gsu.edu | Github Setup | 1 hour | Github | 2020-02-03 | setting up a Github organization and invite.